## Slide 1
Description | Probability | Impact | Response Plan | Responsibility | Status
Risk Register
The new software for XYZ's client has faced an unexpected problem with compatibility and conformity.
3
3
Transfer the task of debugging software to another software developer team under close monitoring from the leader expert
Ryan Hernandez (Team Lead)
Danny Robinson (Software Architect)
Two Software Developers
Closed
Closed
Management Risk.
2
2
Re-evaluate and develop a new plan to upgrade the software to outperform its competitors in the market.
Dawn Smith (Project Manager)
Danny Robinson (Software Architect)
Software Developers
Availability Resources . Insufficient resources for project. Shortage of technical supplies.
1
2
Contact third party vendor
Dawn Smith (Project Manager)
IT Director
Open
External Risk (Market’s rapid development)
1
4
Evaluate and develop a solution plan to address the administrative weaknesses of the Project Manager and his management team.
CEO of XYZ
Financial Director
Dawn Smith (Project Manager)
In progress
Closed
3
4
Develop a new budget for the project to suit the emergency expansion.
CEO of XYZ
Financial Director
Dawn Smith (Project Manager)
Project scope expansion
Closed
2
2
Reschedule a new timetable for the project to suit the unexpected scope expansion.
Dawn Smith (Project Manager)
Ryan Hernandez (Team Lead)
CEO of XYZ
Time is not estimated properly for the project

## Slide 2
STAKEHOLDER REGISTRY
PROJECT NAME
CLIENT
PROJECT DESCRIPTION
XYZ BUSINESS WORKFLOW
XYZ FINANCIAL SERVICES
CUSTOM SOFTWARE SOLUTION TO STREAMLINE SOME WORKFLOWS FOR THEIR WORLDWIDE OFFICES
NAME | ROLE IN PROJECT | POWER | INTEREST | TYPE | Influence on project outcome | NOTE
Dawn Smith | Project Manager | Low | High | Internal | Leading | 
Michael Lee | Software Architect | Low | Medium | Internal | Supportive | 
Danny Robinson | Technical Team Lead | Low | High | Internal | Supportive | 
UTI-1 (TBD) | User Interface Designer | Low | Medium | Internal | Supportive | 
UTI-2 (TBD) | User Interface Designer | Low | Medium | Internal | Supportive | 
Soft-Dev 1 (TBD) | Software Developer | Low | Medium | Internal | Supportive | 
Soft-Dev 2 (TBD) | Software Developer | Low | Medium | Internal | Supportive | 
Soft-Dev 3 (TBD) | Software Developer | Low | Medium | Internal | Supportive | 
Soft-Dev 4 (TBD) | Software Developer | Low | Medium | Internal | Supportive | 
Soft-Test 1 (TBD) | Software Tester | Low | Medium | Internal | Supportive | 
Soft-Test 2 (TBD) | Software Tester | Low | Medium | Internal | Supportive | 
MY-Boss | Project Director | Medium | Medium | Internal | Leading | 
Julia Smith | Product Manager | Low | High | Internal | Supporter | 
Ryan Hernandez | Team Lead | Low | Low | External | Supporter | 
IT (XYZ) | IT Director (XYZ) | High | Low | External | Neutral | 
(XYZ) Finance | Product Manager (XYZ) | High | Low | External | Neutral | 

## Slide 3
Designing
WORK BREAKDOWN STRUCTURE
The Project Director, Project managers and the UI Designer plus UI Developer in the company will set the principal points for developing the initial design and defining the primary frameworks' requirements for the project.
The software architect, the UI designer, and the software developer is to implement ABC workflow V3.0 to meet XYZ's requirements.
The Software tester will evaluate
& test the software initial design.
The last step in this vertical hierarchy is the responsibility of the Product manager ,
and the Software Architect to approve the final UI Design, or send it back to be readjusted
The team lead, product manager,
project manager,
and software architect
will generate
the framework for three new features
for XYZ's new software
The software developer will create
feature one.
then the software tester will finalize it.
The software developer will create
feature two.
then the software tester will finalize it.
The software developer will create
feature three.
then the software tester will finalize it.
The product manager and
the software architect
will assess the compatibility of
the new features
with the new UI.
The last step in this vertical hierarchy is the responsibility of the Product manager ,
and the Software Architect to approve the final developed features, or send it back to be readjusted
The team leads, the product manager,
the project manager, and the software architect
will set up initial points
to customize the developed five features
for the new XYZ software.
The software developers and testers team
customize and test feature one.
The software developers and testers team
customize and test feature two.
The software developers and testers team
customize and test feature three.
The software developers and testers team
customize and test feature four.
The software developers and testers team
customize and test feature five.
The product manager, project manager,
and software architect check
features compatibility with the new UI.
The product manager and the project manager,
and the software architect will approve
the final adjustment for
the new five vustomized features or send it back to be readjusted.
The team leads, the product manager,
the project manager, and the software recheck the new software
the software testers
perform comprehensive and test
for the workability and the performance of the efficiency of their new software.
The IT director and project manager
will lead
the final review on
XYZ Business workflow 1.0 software.
The product manager & the
project manager will authorize the
release of the new product to the client.
Developing 3 features
Customizing 5 features
Software test
The Product manager coordinates with the XYZ finance to get approval for the new software

## Slide 4
The software developers team customize features one to five
RACI’s chart
Task/Delivered | CEO | IT Director | Ryan Hernandez Team Lead | Julia Smith Product Manager | Project Manager Dawn Smith | Michael Lee Software Architect | UI Developer | UI Designer | Software Developers | Software Testers | 
Project managers and the UI Designer plus UI Developer in the company will the principal points for developing the initial design and defining the primary frameworks' based on the ABC workflow v. 3.0
The team lead, product manager project manager,
and software architect will generate the framework for three new features
Requirements Analysis
C
C
R
R
R
I
I
I
I
R
Team Members
External
Internal
Client
XYZ FINANCIAL SERVICES
ABC Solutions
I
I
R
R
R
I
R
I
R
C
I
C
I
I
R
I
I
I
I
R
I
I
I
A
I
I
I
R
I
I
The team leads, the product manager, project manager, and the
software architect will set up the framework to develop and customize the new
five features.
The software developers create new developed features (one to three)
I
I
I
C,I
I
R
I
I
I
I
The software testers check software developer work to send it for approval or send it back for review
I
C
R
R
R
I
I
I
I
R
I
I
I
A
I
I
I
I
I
I
The software testers team test the customized features one to five
I
I
I
C,I
I
R
I
I
I
I
I
C
I
I
I
R
I
I
I
A
I
I
I
I
R
I
I
I
I
A
and the Software Architect review and product manager approve the final developed features
the Product manager ,
and the Software Architect to approve the final developed features
The team leads, the product manager,
the project manager, and the software architect put the final review on the new software
I
I
R
R
R
I
I
I
I
R
The team leads, the product manager,
the project manager, and the software architect put the final review on the new software
I
I
R
R
R
I
I
I
I
R
The team leads, the product manager,
the project manager, and the software architect recheck the new software
C
I
R
I
R
I
I
I
I
A
The IT director and project manager
will lead final review on XYZ Business workflow 1.0 software.
C
R
I
A
I
I
I
I
I
I

## Slide 5
Requirements Analysis
(Delivered by XYZ Business)
START
Mar 1 – Mar 5
1 week
Requirement Analysis
Create framework for 3 new features
Mar 7 – Apr 1
3 weeks
UI design & development
Create framework for customizing 5 new features
Mar 7 – Apr 1
3 weeks
UI design & development
Create test for new feature 1
Apr 4 – June 17
10 weeks
Feature 1 development
Create test for new feature 2
June 20 – Aug 12
8 weeks
Feature 2 development
Create test for new feature 3
Aug 15 – Sep 2
7 weeks
Feature 3 development
Customize test
Apr 4 – May 20
6 weeks
Feature Customization 1
Customize test feature 2
May 23 – June 16
6 weeks
Feature Customization 2
Customize test feature 3
June 20- July 22
4 weeks
Feature Customization 3
Customize test feature 4
July 25 - 19 Aug
3 weeks
Feature Customization 4
Customize test & feature 5
22 Aug – Aug 26
1 weeks
Feature Customization 5
approval for customized 5 features & for developing 3 new features
Sep 5– Aug 12
1 Week
Software System Testing
Release 2
for XYZ Business workflow 1.1
December 15
1 Day
Release
Analyze performance of release 1. fix and finalize software for widespread deployment
Sept 19 - Dec 14
12 weeks
Release preparation
Release 1
for XYZ Business workflow 1.0
September 15
1 Day
Release
Fix, test debug
Finalize checking the XYZ Business workflow 1.1
August 15 – Sept 14
4 weeks
Release preparation
END

## Slide 6
XYZ Business Workflow
status report

## Slide 7
GENERAL PROJECT INFORMATION PROJECT GOAL AND OBJECTIVES • Create a custom software solution to streamline workflows and processes across XYZ Financial Services’ locations. • Use the existing ABC Workflow v3.0 as the framework for the software solution. • Include three new features, customize five of the existing features, and redesign the user interface (UI). • Deliver XYZ Business Workflow v1.0 to two locations by 09/15/2021 (estimated). This version should include all requested features. • Deliver XYZ Business Workflow v1.1 to all locations by 12/15/2021 (estimated). This version will include all requested features.
Project Role and Objective
Generate custom software solution
by using the existing ABC Workflow v3.0 as the framework
1
Develop
three new features
2
customize five of the existing features
3
design
a new user interface
4
5
Objectives
6

## Slide 8
Initial Schedule with Milestones End Dates
2022
Requirement Analysis
Mar 01,22
Mar 04,22
1 Week
3 Week
8 Week
7 Week
6 Week
6 Week
4 Week
1 Week
1 Week
1 Week
1 Week
10 Week
3 Week

## Slide 9
Requirement Analysis
Mar 01,22
Mar 04,22
2022
100%
100%
65%
0%
90%
0%
Week 10
Present Project Status, Accomplishment rate & Schedule Adjustment
0%
0%
0%
0%
0%
0%
Apr 08, 22
Jun, 24, 22
Jun 27, 22
Aug, 26, 2022
Aug, 29, 2022
Sep, 26, 2022
Apr, 8, 22
Week 10
1.1 Release
0%
Aug, 29, 2022
Aug, 29, 2022
Aug, 29, 2022
Aug, 29, 2022
Aug, 29, 2022
Aug, 29, 2022
Aug, 29, 2022
Aug, 29, 2022
Aug, 29, 2022
Aug, 29, 2022
Sep, 30, 2022
Aug, 29, 2022
Aug, 29, 2022
Sep, 30, 2022
10 Week
5 Week
1.5 Week
10w+3d